## Cover Sheet
Test Plan Cover Sheet
Test Plan Name: | WWT COMET Application - Service Contract Management
Owning Group
IT Project No: | 107438
ServiceNow Product | PDCT0010034
Created By: | Lisa Colombo
Creation Date: | 2012-03-16
Last Updated:
Last Updated By:
Version: | 1.0
Primary Analysts: | Lisa Colombo, Izzy Punjasthitkul
Secondary Analysts:
Business Owners | Lauren Getchman, Wendy Bernosky
BSA Managers: | Gary Imig
Reference Documents: | Banyan project folder
Change Record
| Date | Author | Version | Change Description
| 2012-03-16 | Lisa Colombo | 1.0 | Initial Draft

## Overview
Test Plan Overview
Functional / Process Area : | WWT Service Contract Management Web Application (COMET)
Sub-Processes: | 1. Header Search 2. Line search results 3. Contract Details Search Results 4. Filtering search results, recent searches, saved searches 5. Export to Excel (Header, Line, Details, History) 6. Security access testing
WWT Metric Program Name: | All
In Scope: | Searching and exporting for Phase 1 release 4-2-12; External access structure released 7-24-12 but bad data prevents usage
Out of Scope: | Change requests - Phase 2 - Q4 2012
Old Functionality: | Users would search a Cisco tool called Cisco Service Contract Center (CSCC) for contract data by contract number, serial number, etc and export results to Excel
New Functionality: | Internal and external users will have access to a WWT web application which will be easier to use, contain additional data elements like Customer PO# to search, and the new ability to see change history
Assumptions: | None

## Test Plan Summary
Test Plan Scenarios - High Level Summary
# | Scenario Name | Test Phase
|  |  | DEV | INT
1 | Search & Filter | Integration | Pass | Pass
1 | Search by each of the super flexible fields: All, Contract #, Customer PO#, Part #, Part Label, Serial #, Cisco Site ID with one value or multiple up to 100 characters
2 | Search by WWT Customer, Sales Channel, Install Site Customer, Address, and/or Line Status or any combo
3 | Search on Date Range options for End Date, Created, Product PO Date, Maint PO Date, Product PO Ship Date
4 | Check filter on lists after search, select and search again
5 | Check recent searches and saved searches
6 | Search 1999 values in list including not found
2 | Line & Detail Display | Integration | Pass | Pass
1 | Verify Header columns and detail columns
2 | Verify Line columns and detail columns
3 | Freeze and Un-Freeze columns in details screen
4 | Hide and Un-Hide columns in details screen
5 | User roles - external users restricted from internal data
3 | Line Actions
1 | Checkbox lines and perform site move scenarios
2 | Checkbox lines and publish lines and contract
3 | User roles - only internal Admin can publish and do site moves
4 | User roles - only external super user can request changes
5 | User roles - internal user can only view - no actions
6 | User roles - external user can only view (no internal only data), no actions
4 | Export to Excel | Integration | Pass | Pass
1 | Export from Contract, Line, Details and Not Found views
2 | Export has options for Parents Only and Detail Columns
3 | Export has option for History of Changes with Type and Date parameters
5 | External Change Requests
1 | Internal User - Site Moves with XML Integration & Validations
2 | External User Change Requests > Email to Internal Team

## Jitendra_TestMethods
https://www-dev.wwt.com/scm/#/ | https://www-dev.wwt.com/scm/#/
Page Object Type | Test Scenario from Sheet | #Scenario | Scenarion Description | S.No | Return Type | MethodName | Arguments List | My Understanding
HomePage | 1. Search & Filter | 1 | Facets and Buttons > Main Page | 1 | public String | capturingIconHoverOver | (String HoverOverforParticularIcon) | Which ever iconArgument We give it will return the Hover Over of that particular Icon.
HomePage | 1. Search & Filter | 1 |  | 2 | public boolean | verifyingCapturedHoverOver | (String HoverOverforParticularIcon) | Which ever iconArgument We give it will return true if the HoverOver is matched with out expected value. Else it will return false.
HomePage | 1. Search & Filter | 2 | Super Flexfield Searching > All | 3 | public boolean | verifyDisplyTextOnSearchButton | (String textWeWantToVerify) | To Verify whether the name(what ever we give as argument) of the Button is same as "All" or other Types. If same it returns True else It returns false.
HomePage | 1. Search & Filter | 2 |  | 4 | public void | enterContractNumber(s) | (String contractNumber(s)) | Enter into the Contract Number in Super Flex Field.
HomePage | 1. Search & Filter | 2 |  | 5 | public void | clickOnButton | (String buttonName) | Just Click on Button based on the name that we give as argument. Example :- if we give search button - It will click on that particular Button. Or else if we give on customer link, it will clik on customer link.
Search Results Page | 1. Search & Filter | 2 |  | 6 | public Boolean | verifyLinesButton |  | If enabled we ensure that the detault Lines search is displayed.
Search Results Page | 1. Search & Filter | 2 |  | 7. | public int | getSearchResultsPageCount |  | will get the number of pages the particular Search results are availble.
Search Results Page | 1. Search & Filter | 2 |  | 8 |  | No stats will display for the 'All' selection |  | How to Verify whether stats are displayed or not. What is mean by stats.
Search Results Page | 1. Search & Filter | 2.1 | Super Flexfield Searching > All > Review Contract Lines | 9 | public int | verifySearchResultsCount | (List<String> ) | If page number is more than 1. then the count should be 20. The count which it returns should be 20. (each page it contains only 20 results).
Search Results Page | 1. Search & Filter | 2.1 | Super Flexfield Searching > All > Review Contract Lines | 10 | public List<String> | getListOfContractNumbers | (string int) | Argument take which page we have to navigate for results(if 1st page) default int value is 1. It will capture all the Contract Numbers of that particular page.
Search Results Page | 1. Search & Filter | 2.1 | Super Flexfield Searching > All > Review Contract Lines | 11 | public void | ClickOnContractNumber | (String list.get(i)) | based on the given contract number, the contract number gets clicked.
|  | 2.1 | Super Flexfield Searching > All > Review Contract Lines | 12 | public String | getContractNumber | () | Should get the contract Number that displayes on the top of the page.
|  |  |  | 13 | public boolean | verifyContractNumber | (String contractNumer, list.get(i) | the given arguments are (the number we given is the step 10 number and the display numbe in step 11) should match.
|  |  |  | 14 | public String | getWWTCustomerValue | () | Is this a customer name?
|  |  |  | 15 | public Boolean | verifyCustomeName | (String ) | the argument that we give is form the step 13. The name first letter is Captial followed by small letters.

## 1. Search & Filter
ERP Instance
Sub Process Summary : |  | Search the web application for service contract data housed in custom wwt tables |  |  | DEV | [5 empty] | INT
[5 empty] | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed) | [5 empty] | Iteration # 2 (if Iteration # 1 failed)
Step # | Test Case Name | Step Details | Input Data** | Expected Results | Tester | Test Date | Tester | Test Date | Pass/Fail | DEV NOTES | Tester | Test Date | Tester | Test Date | Pass/Fail | INT NOTES
1 | SearchAndFilter_1_0 | Facets and Buttons > Main Page | Hover over all facets and buttons to confirm detail of each selection | Hover functionality exists on facets: WWT Customer, Sales Channel, Install Site Customer, Address, Date Search, Line Status and on buttons: Run Search, Reset Search and Excel Export.
2 | SearchAndFilter_2_0 | Super Flexfield Searching > All | Enter a contract number(s) into the Super Flex Field leaving the filter set to 'All' > search. | The contract number(s) you entered pull back in the search results either by matched or not matched. No stats will display for the 'All' selection.
2.1 | SearchAndFilter_2_1 | Super Flexfield Searching > All > Review Contract Lines. | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched contracts selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
2.2 | SearchAndFilter_2_2 | Super Flexfield Searching > All > Review Contract Header | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case. | First cuolumn displayed is Check boxes, followed by Contract # and then followed by the remaining columns
2.3 | SearchAndFilter_2_3 | Super Flexfield Searching > All > Wildcard Search | Test this field in an open search by any combination of full/partial/multiple values to match and of of the Super Flex Field options. | The values you've selected with either pull back with more than one option to select or not be matched if not present. No stats will display for the 'All' selection. | Test Case - Not Clear - What is the wild card character that I can use to search any value.
3 | SearchAndFilter_3_0 | Super Flexfield Searching > Contract Number | Enter a contract number(s) into the Super Flex Field and select 'Contract #' filter > search. | The contract number(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
3.1 | SearchAndFilter_3_1 | Super Flexfield Searching > Contract Number > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines. | Lines for matched contracts selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
3.2 | SearchAndFilter_3_2 | Super Flexfield Searching > Contract Number > Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case.
3.3 | SearchAndFilter_3_3 | Super Flexfield Searching > Contract Number > Multi-Contract Searching > Manual Entry | Hit Reset, then enter 3 contract numbers manually separated by commas and hit Search. | Those 3 contracts should return
4 | SearchAndFilter_4_0 | Super Flexfield Searching > Customer PO # | Enter customer PO #(s) into the Super Flex Field and select 'Customer PO #' filter > search. | The PO number(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
4.1 | SearchAndFilter_4_1 | Super Flexfield Searching > Customer PO# > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched PO(s) selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
4.2 | SearchAndFilter_4_2 | Super Flexfield Searching > Customer PO #> Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case. | need to check with Gaurav. (, seperated are not able to read fully).
5 | SearchAndFilter_5_0 | Super Flexfield Searching > Part # | Enter part #(s) into the Super Flex Field and select 'Part #' filter > search. | The part #(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
5.1 | SearchAndFilter_5_1 | Super Flexfield Searching > Part # > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched part(s) selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
5.2 | SearchAndFilter_5_2 | Super Flexfield Searching > Part #> Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case.
6 | SearchAndFilter_6_0 | Super Flexfield Searching > Part Label | Enter part #(s) into the Super Flex Field and select 'Part Label' filter > search. | The part label(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
6.1 | SearchAndFilter_6_1 | Super Flexfield Searching > Part Label > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched part labels(s) selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
6.2 | SearchAndFilter_6_2 | Super Flexfield Searching > Part Label > Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case.
7 | SearchAndFilter_7_0 | Super Flexfield Searching > Serial # | Enter serial #(s) into the Super Flex Field and select 'Serial #' filter > search. | The serial(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
7.1 | SearchAndFilter_7_1 | Super Flexfield Searching > Serial # > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched serial(s) selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
7.2 | SearchAndFilter_7_2 | Super Flexfield Searching > Serial #> Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case.
8 | SearchAndFilter_8_0 | Super Flexfield Searching > Site ID | Enter serial #(s) into the Super Flex Field and select 'Site ID' filter > search. | The site id(s) you entered pull back in the search results either by matched or not matched. Check the Stats tab to confirm your selection results match. Include scenarios for both single and multiple searches.
8.1 | SearchAndFilter_8_1 | Super Flexfield Searching > Site ID > Review Contract Lines | Screen from above search will default to the lines of the contracts selected. Review lines | Lines for matched site id(s) selected display and can be scrolled through. Check link for contract # to confirm it takes you to the correct contract tab. Make sure the WWT Customer value is upper/lower case.
8.2 | SearchAndFilter_8_2 | Super Flexfield Searching > Site ID > Review Contract Headers | Click the 'Contracts' button to see the contract headers | Selection of the button takes you to the contract headers view which should be ordered first by the 'Order By Customer', then by 'Service Level'. Make sure values are comma separated when more than one value is present in the field. Make sure the WWT Customer value is upper/lower case.
9 | SearchAndFilter_9_0 | Facet Searching > Customer > Single | Select a Customer from the 'Customer' facet and select the search button. Note the number in parenthesis next to the customer's name. Also test out the 'contains' functionality for partial searching | The matched number of contracts shown from the initial search request should return.
9.1 | SearchAndFilter_9_1 | Facet Searching > Customer > Multiple | Test this field in an open search by any combination of full/partial/multiple values as well as the add all and remove all buttons. | All combinations of customer searches and filters pull back the number of contracts expected.
10 | SearchAndFilter_10_0 | Facet Searching > Sales Channel > Single | Select one sales channel from the 'Sales Channel' facet and select the search button. Note the number in parenthesis next to the name. Also test out the 'contains' functionality for partial searching | The matched number of contracts shown from the initial search request should return.
10.1 | SearchAndFilter_10_1 | Facet Searching > Sales Channel > Multiple | Test this field in an open search by any combination of full/partial/multiple values as well as the add all and remove all buttons. | All combinations of sales channel searches and filters pull back the number of contracts expected.
11 | SearchAndFilter_11_0 | Facet Searching > Install Site Customer > Single | Select one site address from the 'Install Site Customer' facet and select the search button. Note the number in parenthesis next to the name. Also test out the 'contains' functionality for partial searching | The matched number of contracts shown from the initial search request should return.
11.1 | SearchAndFilter_11_1 | Facet Searching > Install Site Customer > Multiple | Test this field in an open search by any combination of full/partial/multiple values as well as the add all and remove all buttons. | All combinations of install site customer searches and filters pull back the number of contracts expected including examples like 'BURT' which may include apostrophes in the name.
12 | SearchAndFilter_12_0 | Facet Searching > Address > Single | Select an address from the 'Address' facet and select the search button. Note the number in parenthesis next to the value. Also test out the 'contains' functionality for partial searching | The matched number of contracts shown from the initial search request should return.
12.1 | SearchAndFilter_12_1 | Facet Searching > Customer > Multiple | Test this field in an open search by any combination of full/partial/multiple values as well as the add all and remove all buttons. | All combinations of address searches and filters pull back the number of contracts expected.
12.3 | SearchAndFilter_12_2 | Facet Searching > Address > street value | 15000. Also test out the 'contains' functionality for partial searching | Should return address values with 15000 in the street address or part of the zip code value; Select 3 and see if the addresses in the Detail results all contain that value.
12.4 | SearchAndFilter_12_3 | Facet Searching > Address > street name | WELDON. Also test out the 'contains' functionality for partial searching | Should return address values with Weldon in the street name; Select 3 and see if the addresses in the Detail results all contain that value
12.4 | SearchAndFilter_12_4 | Facet Searching > Address > City name | MONTEREY. Also test out the 'contains' functionality for partial searching | Should return address values with Monterey in the street name or city; Select 3 and see if the addresses in the Detail results all contain that value
12.5 | SearchAndFilter_12_5 | Facet Searching > Address > State name | MT. Also test out the 'contains' functionality for partial searching | Should return address values with MT in the street name or city name; Select 3 and see if the addresses in the Detail results all contain that value
12.6 | SearchAndFilter_12_6 | Facet Searching > Address > Zip Code | 66219. Also test out the 'contains' functionality for partial searching | Should return address values with 66219 in the zip code; Select 3 and see if the addresses in the Detail results all contain that value
12.7 | SearchAndFilter_12_7 | Facet Searching > Address > Country | Search on one customer, then enter a month's date range and search again. If you get no data, open up a contract to see some dates and use that as your range. Also test out the 'contains' functionality for partial searching | Should return address values with Angola in the street, city or country; Select 3 and see if the addresses in the Detail results all contain that value.
13 | SearchAndFilter_13_0 | Facet Searching > Date Search > Date Field Validation | Check the calendar date field validation by selecting the month, year and left/right arrows in all date search filters. | Selection of all variables allows the user to select a date and execute the search.
13.1 | SearchAndFilter_13_1 | Facet Searching > Date Search > Creation Date range | 01-MAY-2012 to 31-MAY-2012 | Run this query in appropriate environment to find a good date range for testing. Then check your output in Details to see that the Creation date of the lines returned is within your selected range. You can also Export Details from the initial search results and view the dates in Excel. select trunc(creation_date), count(rowid) from apps.wwt_scm_contract_line where publish_flag is null group by trunc(creation_date)
13.2 | SearchAndFilter_13_2 | Facet Searching > Date Search > Creation Date Search Logic for Parents/Children | Any search criteria should be applied to both parent and child items however the app should only return the parent in the search. The child should be highlighted under that parent when expanded. | Search results pull the parent of the child and the child is highlighted under the parent when expanded.
13.3 | SearchAndFilter_13_3 | Facet Searching > Date Search > Product PO Date Range | Search on one customer, then enter a month's date range and search again. If you get no data, open up a contract to see some dates and use that as your range. | Check that the dates for that column in the Details screen are all within the date range you entered.
13.4 | SearchAndFilter_13_4 | Facet Searching > Date Search > Product PO Date Search Logic for Parents/Children | Any search criteria should be applied to both parent and child items however the app should only return the parent in the search. The child should be highlighted under that parent when expanded. | Search results pull the parent of the child and the child is highlighted under the parent when expanded.
13.5 | SearchAndFilter_13_5 | Facet Searching > Date Search > Maintenance PO Date Range | Search on one customer, then enter a month's date range and search again. If you get no data, open up a contract to see some dates and use that as your range. | Check that the dates for that column in the Details screen are all within the date range you entered.
13.6 | SearchAndFilter_13_6 | Facet Searching > Date Search > Maintenance PO Date Search Logic for Parents/Children | Any search criteria should be applied to both parent and child items however the app should only return the parent in the search. The child should be highlighted under that parent when expanded | Search results pull the parent of the child and the child is highlighted under the parent when expanded.
13.7 | SearchAndFilter_13_7 | Facet Searching > Date Search > Product PO Ship Date Range | Search on one customer, then enter a month's date range and search again. If you get no data, open up a contract to see some dates and use that as your range. | Check that the dates for that column in the Details screen are all within the date range you entered.
13.8 | SearchAndFilter_13_8 | Facet Searching > Date Search > Product PO Date Search Logic for Parents/Children | Any search criteria should be applied to both parent and child items however the app should only return the parent in the search. The child should be highlighted under that parent when expanded | Search results pull the parent of the child and the child is highlighted under the parent when expanded
13.9 | SearchAndFilter_13_9 | Facet Searching > Date Search > End Date Range | Search on one customer, then enter a month's date range and search again. If you get no data, open up a contract to see some dates and use that as your range. | Check that the dates for that column in the Details screen are all within the date range you entered
13.1 | SearchAndFilter_13_10 | Facet Searching > Date Search > End Date Search Logic for Parents/Children | Any search criteria should be applied to both parent and child items however the app should only return the parent in the search. The child should be highlighted under that parent when expanded | Search results pull the parent of the child and the child is highlighted under the parent when expanded
13.11 | SearchAndFilter_13_11 | Facet Searching > Date Search > Search combo customer, publish status and creation date range | Select a customer name from previous output, leave creation date range, and select Line Status = "Needs Review" | Check contract line status in Details page to verify publish status is blank; Capital One has Needs Review lines in INT as of 7/19/12
14 | SearchAndFilter_14_0 | Facet Searching > Line Status > Line Status > Expired Lines | Select any customer, search all first, then change line status to Include Expired and Search again. | The number of rows should increase when expired rows are included. If they don't, try a couple of different customers. FBI has expired in INT as of 7/19/12.
15 | SearchAndFilter_15_0 | Facet Searching > Line Status > Line Status > Terminated Lines | Select any customer, search all first, then change line status to Include Terminated and Search again. | The number of rows should increase when terminated rows are included. If they don't, try a couple of different customers.
16 | SearchAndFilter_16_0 | Facet Searching > Line Status > Publish Flag Filter > Needs Review Lines > Unfiltered | Select the 'Needs Review' checkbox and run a search | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Needs' Review' status.
16.1 | SearchAndFilter_16_1 | Facet Searching > Line Status > Publish Flag Filter > Needs Review Lines > Filtered | Test out any other facet search filter, run a search and then select the 'Needs Review' checkbox and run the search again. | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Needs' Review' status within the filter you selected.
17 | SearchAndFilter_17_0 | Facet Searching > Line Status > Publish Flag Filter > Published > Unfiltered | Select the 'Published' checkbox and run a search | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Published' status.
17.1 | SearchAndFilter_17_1 | Facet Searching > Line Status > Publish Flag Filter > Published > Filtered | Test out any other facet search filter, run a search and then select the 'Published' checkbox and run the search again. | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Published' status within the filter you selected.
18 | SearchAndFilter_18_0 | Facet Searching > Line Status > Publish Flag Filter > Not Published > Unfiltered | Select the 'Not Published' checkbox and run a search | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Not Published' status.
18.1 | SearchAndFilter_18_1 | Facet Searching > Line Status > Publish Flag Filter > Not Published > Filtered | Test out any other facet search filter, run a search and then select the 'Not Published' checkbox and run the search again. | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'Not Published' status within the filter you selected.
19 | SearchAndFilter_19_0 | Facet Searching > Line Status > End of Support > Unfiltered | Select the 'End of Support' checkbox and run a search | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'End of Support' status.
19.1 | SearchAndFilter_19_1 | Facet Searching > Line Status > End of Support > Filtered | Test out any other facet search filter, run a search and then select the 'End of Suport' checkbox and run the search again. | Click into the 'Contracts' tab and confirm the results only pull back contracts with lines in 'End of Support' status within the filter you selected.
20 | SearchAndFilter_20_0 | Stats Tab > Match found | From the search above, review the 'Stats' tab | You should see a green number on the 'Stats' tab noting a mached value. Click on that tab to review
21 | SearchAndFilter_21_0 | Stats Tab > Match Not found | Hit Reset, enter a contract number that does not exist. | You should see a red number on the 'Stats' tab noting an unmached value. Click on that tab to review
22 | SearchAndFilter_22_0 | Sorting | Each output column should sort up and down
23 | SearchAndFilter_23_0 | Performance | 91735015 | < 5 seconds to return - this contract has > 100,000 rows
24 | SearchAndFilter_24_0 | External Restrictions | Log in as edj@wwt.com, pass123 | External users should not see search fields Product PO or Maint PO in Superflexible drop down
24.1 | SearchAndFilter_24_1 | External Restrictions | edj@wwt.com is tied to Edward Jones; markwill@cisco.com is tied to Edward Jones and Savvis | External user should default to their mapped WWT customer values and see no others
24.2 | SearchAndFilter_24_2 | External Restrictions | Select several sites and Search | External user values in Sites and Addresses should only be those tied to their WWT customer in the data; Validate output is only for sites selected in search
24.3 | SearchAndFilter_24_3 | External Restrictions | External user should not see Sales Channel search field | External user should not see Sales Channel search field
24.4 | SearchAndFilter_24_4 | External Restrictions | Enter a date range to cover one of the earliest end dates shown in the full customer search results from Contract tab | External user should only see Contract End Date range option; All other date range sections for Creation Date, Product PO Date, Maintenance PO Date, Product PO Ship Date should be hidden from the external user; Output in Lines tab should only show end dates in range entered | Creation Date is displaying as Line Creation Date, ,is that correct?
24.5 | SearchAndFilter_24_5 | External Restrictions | Select "End of Support" and Search | External user should not see Publish statuses in Line Status list of values (Published, Not Published, Needs Review). The only line statuses they should see are Expired, Terminated and End of Support; Output in Details page should only contain lines that have an End of Support date value. | Getting Blanks in End of Support date Value?
24.6 | SearchAndFilter_24_6 | External Restrictions | External user should not see counts of published lines in Contract header output; The only columns in the Contract output will be WWT Customer, Contract #, Service Level and Earliest End Date | External user should not see counts of published lines in Contract header output; The only columns in the Contract output will be WWT Customer, Contract #, Service Level and Earliest End Date

## 2. Line & Detail Display
ERP Instance |  |  | DEVERP
Sub Process Summary : |  |  | The Lines tab should return all lines for the contracts found from the search criteria. Then lines will reduce based on further search criteria applied. |  | DEV |  |  |  |  | INT
[5 empty] | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed) |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed)
Step # |  | Step Details | Input Data | Expected Results | Tester | Test Date | Tester | Test Date | Pass/Fail | Tester | Test Date | Tester | Test Date | Pass/Fail | Notes
1 | LineAndDetailDisplay_1_0 | Internal user login | Internal user account | Internal Login defaults to dashboard
1.1 | LineAndDetailDisplay_1_1 | Line Details Page Display | Select a customer and execute a search | Search response takes you into the contract line details page for that customer
1.2 | LineAndDetailDisplay_1_2 | Facets and Buttons > Lines Page | Hover functionality exists on facets: WWT Customer, Sales Channel, Install Site Customer, Address, Date Search, Line Status and on buttons: Run Search, Reset Search and Excel Export | Facet and button detail displays when you hover over them on the lines detail page
1.3 | LineAndDetailDisplay_1_3 | Column Sorting | Sort each column ascending and descending | Ensure they all work in Chrome, IE and Firefox
1.4 | LineAndDetailDisplay_1_4 | Contract link in lines page | Hot link from contract number to details | Should open Detail screen for that Contract
1.5 | LineAndDetailDisplay_1_5 | Line detail data confirmation | Ensure output matches Toad query | Compare column by column data to Toad output for given contract #
1.6 | LineAndDetailDisplay_1_6 | Check for Word Wrapping in Site Name column | Sites exceeding single line have continuation dots and a hover to display entire value | Format and hover on line displays as expected
1.7 | LineAndDetailDisplay_1_7 | Check for Word Wrapping in Site Address column | Addresses exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
1.8 | LineAndDetailDisplay_1_8 | Check for Word Wrapping in Site City column | Cities exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
1.9 | LineAndDetailDisplay_1_9 | Check for Word Wrapping in Site Country column | Countries exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
1.1 | LineAndDetailDisplay_1_10 | Hide columns in output display | Hide sections by selecting the gear button and checking the columns you wish to remove from your output. | Ensure that it's gone.
1.11 | LineAndDetailDisplay_1_11 | Unhide columns in output display | Un-hide sections by selecting the gear button and un-checking the columns you wish to reappear in your output. Test both hiding some as well as all column scenarios. | Section should display back again
1.12 | LineAndDetailDisplay_1_12 | Freeze columns in output display | Freeze sections by selecting the gear button and 'pinning' the columns you wish to freeze in your output. | Ensure that the columns have frozen by scrolling
1.13 | LineAndDetailDisplay_1_13 | Un-Freeze columns in output display | Un-Freeze sections by selecting the gear button and 'un-pinning' the columns you wish to un-freeze in your output. Test both freezing some as well as all column scenarios. | Ensure that the columns have un-frozen by scrolling
1.14 | LineAndDetailDisplay_1_14 | Sort on Start Date and End Date | Contract has multiple dates within it's rows | Check that the "earliest start and end date" in header of page matches what shows in the sort as the earliest date. Earliest end date could be hidden in a child item tho. Need query to check.
2 | LineAndDetailDisplay_2_0 | External user login | Login as external user scmdemo@wwt.com, pass123 | External login defaults to dashboard
2.1 | LineAndDetailDisplay_2_1 | Line Details Page Display | Confirm the default customer pulls back from your executed search | Search response takes you into the contract line details page for that customer. No changes to Line layout for external than internal; both internal and external see these columns: Site Customer, Site ID, Contract Number, Service Level, Serial Number, Part Number, Qty, Start Date, End Date
2.2 | LineAndDetailDisplay_2_2 | Facets and Buttons > Lines Page | Hover functionality exists on facets: WWT Customer, Install Site Customer, Address, Date Search, Line Status and on buttons: Run Search, Reset Search and Excel Export | Facet and button detail displays when you hover over them on the lines detail page
2.3 | LineAndDetailDisplay_2_3 | Column Sorting | Sort each column ascending and descending. | Ensure they all work in Chrome, IE and Firefox
2.4 | LineAndDetailDisplay_2_4 | Contract link in lines page | Hot link from contract number to details. | Should open Detail screen for that Contract
2.5 | LineAndDetailDisplay_2_5 | Line detail data confirmation | Ensure output matches Toad query. | Compare column by column data to Toad output for given contract #
2.6 | LineAndDetailDisplay_2_6 | Check for Word Wrapping in Site Name column | Sites exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
2.7 | LineAndDetailDisplay_2_7 | Check for Word Wrapping in Site Address column | Addresses exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
2.8 | LineAndDetailDisplay_2_8 | Check for Word Wrapping in Site City column | Cities exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
2.9 | LineAndDetailDisplay_2_9 | Check for Word Wrapping in Site Country column | Countries exceeding single line have continuation dots and a hover to display entire value. | Format and hover on line displays as expected
2.1 | LineAndDetailDisplay_2_10 | Hide columns in output display | Hide sections by selecting the gear button and checking the columns you wish to remove from your output. | Ensure that it's gone.
2.11 | LineAndDetailDisplay_2_11 | Unhide columns in output display | Un-hide sections by selecting the gear button and un-checking the columns you wish to reappear in your output. Test both hiding some as well as all column scenarios. | Section should display back again
2.12 | LineAndDetailDisplay_2_12 | Freeze columns in output display | Freeze sections by selecting the gear button and 'pinning' the columns you wish to freeze in your output | Ensure that the columns have frozen by scrolling
2.13 | LineAndDetailDisplay_2_13 | Un-Freeze columns in output display | Un-Freeze sections by selecting the gear button and 'un-pinning' the columns you wish to un-freeze in your output. Test both freezing some as well as all column scenarios. | Ensure that the columns have un-frozen by scrolling
2.14 | LineAndDetailDisplay_2_14 | Sort on Start Date and End Date | Contract has multiple dates within it's rows | Check that the "earliest start and end date" in header of page matches what shows in the sort as the earliest date. Earliest end date could be hidden in a child item tho. Need query to check.
2.15 | LineAndDetailDisplay_2_15 | External Restrictions - columns displayed | scmdemo@wwt.com, pass123 | External users should not see the following fields in the output: Publish Flag or checkbox, Sales Channel, Product PO#, Product PO Date, Maint PO# , Maint PO Date, Product PO Ship Date, Creation Date
2.16 | LineAndDetailDisplay_2_16 | External Restrictions - buttons |  | External users should not have an Action button for Publishing;
Note on P20: StewartV: select * from apps.wwt_scm_contract_line where contract_id in (select contract_id from apps.wwt_scm_contract_header where contract_number = 92225193 )order by end_date asc

## 3. Line Actions
Sub Process Summary : |  |  |  | DEV |  |  |  |  | INT
|  |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed) |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed)
Step # | Step Details | Input Data | Expected Results | Tester | Test Date | Tester | Test Date | Pass/Fail | Tester | Test Date | Tester | Test Date | Pass/Fail | Notes
Test Overview:
1 | Change Site For Selected | Search on a WWT Customer and open a contract | Contract selected opens and lines display
1.1 | Make note of existing site id, city, and country for first green status row shown
1.2 | Select that line that is in green status, check box, Action > Move Site for Selected |  | New screen opens to search a "to" site
1.3 | Search new site for country <> existing one | if US, search Japan | Get results with Japan in them
1.4 | Click Move |  | Should get "Validation Failed" error with note below saying "Attempting site move to different country"
1.5 | Click Cancel |  | Go back to Contract Details screen
1.6 | Check box for same line again, Action > Move Site for Selected
1.7 | Search for existing site id |  | Should display current address for item
1.8 | Click Move |  | Should get "Validation Failed" error with note below saying "From and To sites are the same".
1.9 | Click Cancel |  | Go back to Contract Details screen
1.1 | Check box for same line again
1.11 | Search for new site by same city | i.e. Newport Beach | Get results for all addresses with Newport Beach in them
1.12 | Click Move on a new site |  | Should get "Validation Successful" with screen showing "from" and "to" site and item being moved
1.13 | Click "Confirm Site Move" |  | Should get screen site move was successfully sent
1.14 | Click "Return to Contracts" |  | Line should change to yellow Status for Pending Cisco confirmation
1.15 | XML message is sent to Cisco |  | Check myWebMethods for 6A1 outbound
2 | Publish/Unpublish status | Within both the contracts tab and lines tab, confirm that under the actions drop down, you see actions for Publish and Unpublish respectively
2.1 | Internal Admin toggle Publish/Unpublish status | Select rows of a contract in Detail page,check box to left and select Action > Publish or Unpublish | Publish flag should change; lines table should show last updated by name and date; audit table should record the change from x to y status;
2.2 | Exp/Term Counts in Publish/Unpublish filtering | Publish/Unpublish counts should not include Exp/Term lines unless user includes those options from Line Status | Publish flag should change; lines table should show last updated by name and date; audit table should record the change from x to y status based upon selection made;
2.3 | Re-query lines that had publish status change | Input contract # on main search | Count of lines published and not published should have changed; Open Details to view line level status
2.4 | Internal User restrictions |  | An internal user should see the published counts on the initial search results, and when clicking into a contract Detail screen, should see the Publish Flag column but will have no checkbox and no Action drop down so that they cannot edit publish flag for any rows.

## 4. Export to Excel and History
ERP Instance |  | DEVERP
Sub Process Summary : |  |  |  | DEV |  |  |  |  | INT
|  |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed) |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed)
Step # | Step Details | Input Data | Expected Results | Tester | Test Date | Tester | Test Date | Pass/Fail | Tester | Test Date | Tester | Test Date | Pass/Fail | Notes
Test Overview:
1 | Export to Excel Validation > Headers Only | Search on WWT customer on main page > Edward Jones | Several contracts with > 200,000 total lines | [10 empty] | change test point per new export logic
1.1 | Click Export from Headers Only option | The Excel progress bar within Comet should close automatically when the file is complete. | New excel file should open with 1 tab for Contract header details with columns shown as WWT Customer, Contract #, Service Level, Earliest End Date, Not Published, Review Total | [10 empty] | change test point per new export logic
2 | Export to Excel Validation > Lines-Parents Only | Search on WWT customer on main page > Edward Jones | Several contracts with > 200,000 total lines | [10 empty] | change test point per new export logic
2.1 | Click Export from Lines-Parents Only option | The Excel progress bar within Comet should close automatically when the file is complete. | New excel file should open with 1 tab for parent, stand alones and orphans only details with columns shown in the same order as the app UI starting with column A as Contract # | [10 empty] | change test point per new export logic
3 | Export to Excel Validation > All Lines | Search on WWT customer on main page > Edward Jones | Several contracts with > 200,000 total lines | [10 empty] | change test point per new export logic
3.1 | Click Export from All Lines option | The Excel progress bar within Comet should close automatically when the file is complete. | New excel file should open with 1 tab for all lines, parents, children, stand alones and orphan details with columns shown in the same order as the app UI starting with column A as Contract # | [10 empty] | change test point per new export logic
4 | Export to Excel Validation > Filtered Lines | Search on a customer and filter to one contract | All contract lines results should return in Excel, not just original search results | [10 empty] | change test point per new export logic
4.1 | Filter further from contract to specific sites/serials, then export |  | All filtered contract lines results should return in Excel, not just original search results | [10 empty] | change test point per new export logic
4.2 | If your original search was at a line level value (serial, site), click "Show All Contract Lines" in Details tab then Export | Serial: FOC16014WQH for Contract: 91994501 | All contract lines results should return in Excel, not just original search results | [10 empty] | change test point per new export logic
4.3 | Select "Contract Details" export option from Contract/Lines output | WWT Customer = Anadarko | File should contain Contract Header tab and then Contract Details tab with all the same columns in the Detail view (i.e. PO#s) - 24 col as of 5/22/12 in Dev | [10 empty] | change test point per new export logic
5 | Export to Excel Validation > History | Search on WWT customer on main page > Edward Jones | Several contracts with > 200,000 total lines | [10 empty] | change test point per new export logic
5.1 | Click Export from History option | The Excel progress bar within Comet should close automatically when the file is complete. | New excel file should open with 1 tab for all lines, parents, children, stand alones and orphan details with columns shown in the same order as the app UI starting with column A as Contract # | [10 empty] | change test point per new export logic
5.2 | Compare Excel output to database | apps.wwt_scm_change_audit_detail | New excel file should match the history detail in what is seen in the database for selected contract including date changes, publish flags, site moves, status changes | [10 empty] | change test point per new export logic
5.3 | History Export Testing | Run search on contract 92032919 and 90329824 in DEV; | These 2 contracts have a combination of history changes to cover the types available - End of Support Date, Install Site ID, Service Level Status, Start Date, End Date, Transaction Name | [10 empty] | change test point per new export logic
5.4 | History Export Testing | Search on Andarko, then pick 2 sites and run History Export | Should produce file and not error | [10 empty] | change test point per new export logic
5.5 | History Export Testing | Search on Andarko, then pick 2 addresses and run History Export | Should produce file and not error | [10 empty] | change test point per new export logic
6 | External restrictions | log in as edj@wwt.com, pass123 | [11 empty] | change test point per new export logic
6.1 | External restrictions - Unfiltered search | Search without any parameters except the defaulted "WWT Customer" of "Edward Jones" | For export from Contract or Lines tab, the external user would not see the Published Line Counts per contract on the Contract tab. The lines data export is the same for all users. | [10 empty] | change test point per new export logic
6.2 | External restrictions - Unfiltered search | Open one of the contracts from search results into the Details tab and Export. | For the Details export, the user should not see columns that they don't see in the UI - i.e. Publish Flag, Product PO, Maint PO, Sales Channel, etc. | [10 empty] | change test point per new export logic
7 | External restrictions - Filtered | Export again from Details but click "Parents Only" in the Export pull-down | Ensure that the P/C column only has "P" values in it in Excel. | [10 empty] | change test point per new export logic

## 5. External Change Requests
Sub Process Summary : |  |  |  | DEV |  |  |  |  | INT
|  |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed) |  |  | Iteration #1 |  | Iteration # 2 (if Iteration # 1 failed)
Step # | Step Details | Input Data | Expected Results | Tester | Test Date | Tester | Test Date | Pass/Fail | Tester | Test Date | Tester | Test Date | Pass/Fail | Notes
Test Overview:
1 | Log in as an external customer | scmdemo@wwt.com
1.1 | Click search to get all contracts back |  | 4 contracts should return in Dev
1.2 | Open first one into Details tab
1.3 | Click on first line's checkbox
1.4 | Click Action > RMA/Serial | Enter fake RMA#, new Serial and comments | Screen should allow entry
1.5 | Hit Submit |  | Email is sent to requester and internal vendor alliance team and Lisa C
1.6 | Check email content for external user |  | Should summarize the requested change and state that WWT will let user know when change is processed
1.7 | (Process: WWT VA team contacts Cisco to make the change manually, update flows through existing integrations for daily changes and is reflected in Comet)
2 | Check box, select Action > Remove from Contract
2.1 | Select a Reason for removal (Tech Refresh, Decommission)
2.2 | Enter Comment
2.3 | Hit Submit |  | Email is sent to requester and internal vendor alliance team and Lisa C
2.4 | Check email content for external user and internal team |  | Should summarize the requested change and state that WWT will let user know when change is processed
3 | Check box, select Action > Change Service Level
3.1 | Enter new service level
3.2 | Screen displays old service level for item moving
3.3 | Hit Submit |  | Email is sent to requester and internal vendor alliance team and Lisa C
3.4 | Check email content for external user and internal team |  | Should summarize the requested change and state that WWT will let user know when change is processed
4 | Review lines in confirmed status for sites mapped to customer |  | Lines displayed are those in confirmed status and mapped to customer/site selected. **Working development in progress to limit the sites an external user can choose, based on the customer they are tied to. Refer to Trello card named 'Modify Site Move action to work for external users but limit site search to only sites in their mapped contracts' - Sprint 5
4.1 | Check box, select Action > Site Move Request
4.2 | Enter new address and comments
4.3 | Hit Submit |  | Email is sent to requester and internal vendor alliance team and Lisa C
4.4 | Check email content for external user and internal team |  | Should summarize the requested change and state that WWT will let user know when change is processed
5 | Check box, select Action > Map Contracts to Customer
5.1 | Locate a contract to be mapped |  | contract returns in search
5.2 | Click Map Contracts to Customer button
5.3 | Search for customer to map contract to
5.4 | Select Map Contracts To button
5.5 | Confirm in database that contract mapped to customer |  | wwt_sales_scm.wwt_scm_contract_cust_map